## WBS
ID | Task Mode | Task Name | Description | Duration | Start | Finish | Predecessor(s) | Resource Names | Resources Needed / Milestone
0 | Auto Scheduled | MCC Construction Mobile Management System | Complete MCC Construction WIL project | 119 days | 2026-05-06 | 2026-10-19 |  | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Full Project
1.0 | Manually Scheduled | Project Initiation | Define scope, meet client and establish project plan | 8 days | 2026-05-06 | 2026-05-15 |  | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | MS Teams, Word, Client Meetings
1.1 | Manually Scheduled | Define project objectives and scope | Define project objectives, deliverables and boundaries | 2 days | 2026-05-06 | 2026-05-07 |  | Kaydyn, Ariana | Word, Teams
1.2 | Manually Scheduled | Initial client meeting | Meet MCC Construction and gather initial business information | 1 day | 2026-05-08 | 2026-05-08 | 1.1 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Teams, Meeting Notes
1.3 | Manually Scheduled | Establish project plan | Create schedule, responsibilities and project approach | 4 days | 2026-05-11 | 2026-05-14 | 1.2 | Kaydyn, Wesley, Adrian | MS Project, Word
1.4 | Manually Scheduled | Project Approval | Obtain approval to proceed | 0 days | 2026-05-15 | 2026-05-15 | 1.3 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Project Approval
2.0 | Manually Scheduled | Requirements Analysis | Research organisation and define requirements | 20 days | 2026-05-18 | 2026-06-12 | 1.4 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Research, Word, Client Input
2.1 | Manually Scheduled | Organisation research | Understand MCC Construction operations and users | 3 days | 2026-05-18 | 2026-05-20 | 1.4 | Ariana, Adrian | Internet, Company Information
2.2 | Manually Scheduled | Construction industry research | Research construction software and industry practices | 3 days | 2026-05-21 | 2026-05-25 | 2.1 | Ariana, Wesley | Academic Sources, Internet
2.3 | Manually Scheduled | Functional requirements | Document system functions and modules | 4 days | 2026-05-26 | 2026-05-29 | 2.2 | Ariana, Kaydyn, Jemaine | Word, Client Notes
2.4 | Manually Scheduled | Non-functional requirements | Define security, usability, performance and reliability requirements | 3 days | 2026-06-01 | 2026-06-03 | 2.3 | Wesley, Jemaine | Security/Performance Research
2.5 | Manually Scheduled | User roles and permissions | Define Administrator, Manager and Worker access | 2 days | 2026-06-04 | 2026-06-05 | 2.4 | Ariana, Kaydyn | Word
2.6 | Manually Scheduled | Requirements documentation | Compile and review requirement artefacts | 4 days | 2026-06-08 | 2026-06-11 | 2.5 | Ariana, Adrian, Wesley | Word
2.7 | Manually Scheduled | Requirements Complete | Requirements phase completion | 0 days | 2026-06-12 | 2026-06-12 | 2.6 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Requirements Complete
3.0 | Manually Scheduled | UX/UI and Prototype | Design user experience and high-fidelity prototype | 20 days | 2026-06-15 | 2026-07-10 | 2.7 | Ariana, Thersh, Adrian | Figma
3.1 | Manually Scheduled | Develop user stories | Write user stories for key roles and functionality | 3 days | 2026-06-15 | 2026-06-17 | 2.7 | Ariana, Adrian | Word, Figma
3.2 | Manually Scheduled | Create UX journey maps | Map Worker and Manager journeys | 2 days | 2026-06-18 | 2026-06-19 | 3.1 | Ariana, Thersh | Figma
3.3 | Manually Scheduled | Design mobile navigation structure | Define bottom navigation and manager menu | 2 days | 2026-06-22 | 2026-06-23 | 3.2 | Thersh, Ariana | Figma
3.4 | Manually Scheduled | Create low-fidelity wireframes | Design initial mobile screen layouts | 4 days | 2026-06-24 | 2026-06-29 | 3.3 | Thersh, Ariana | Figma
3.5 | Manually Scheduled | Create high-fidelity mobile prototype | Create polished interactive Manager and Worker screens | 7 days | 2026-06-30 | 2026-07-08 | 3.4 | Thersh, Ariana, Adrian | Figma
3.6 | Manually Scheduled | Prototype review and improvements | Review prototype and incorporate feedback | 2 days | 2026-07-09 | 2026-07-10 | 3.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Figma, Client Feedback
3.7 | Manually Scheduled | Prototype Approved | Prototype approval milestone | 0 days | 2026-07-10 | 2026-07-10 | 3.6 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Prototype Approved
4.0 | Manually Scheduled | System Analysis and Design | Create UML analysis and design artefacts | 10 days | 2026-07-13 | 2026-07-24 | 3.7 | Kaydyn, Jemaine, Wesley, Adrian | PlantUML, Draw.io
4.1 | Manually Scheduled | Domain model | Create UML domain class diagram | 2 days | 2026-07-13 | 2026-07-14 | 3.7 | Jemaine, Adrian | PlantUML
4.2 | Manually Scheduled | Design class diagram | Create implementation-level UML class diagram | 3 days | 2026-07-15 | 2026-07-17 | 4.1 | Jemaine, Kaydyn | PlantUML
4.3 | Manually Scheduled | Sequence diagrams | Create UML sequence diagrams for critical flows | 3 days | 2026-07-20 | 2026-07-22 | 4.2 | Wesley, Kaydyn, Adrian | PlantUML
4.4 | Manually Scheduled | State diagrams | Create UML state diagrams for critical entities | 2 days | 2026-07-23 | 2026-07-24 | 4.3 | Wesley, Adrian | PlantUML
4.5 | Manually Scheduled | System Design Complete | System design completion milestone | 0 days | 2026-07-24 | 2026-07-24 | 4.4 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: System Design Complete
5.0 | Manually Scheduled | Database Design | Design and implement relational data model | 6 days | 2026-07-27 | 2026-08-03 | 4.5 | Jemaine, Kaydyn | Azure SQL, Draw.io
5.1 | Manually Scheduled | Identify database entities | Identify core entities from system requirements | 1 day | 2026-07-27 | 2026-07-27 | 4.5 | Jemaine, Kaydyn | Requirements, SQL
5.2 | Manually Scheduled | Define attributes and relationships | Define entity fields, PKs, FKs and relationships | 2 days | 2026-07-28 | 2026-07-29 | 5.1 | Jemaine, Kaydyn | SQL, ERD Tools
5.3 | Manually Scheduled | Create ERD | Create detailed crow's foot ERD | 2 days | 2026-07-30 | 2026-07-31 | 5.2 | Jemaine, Adrian | Draw.io/Figma
5.4 | Manually Scheduled | Implement initial database schema | Create initial Azure SQL database structure | 1 day | 2026-08-03 | 2026-08-03 | 5.3 | Jemaine | Azure SQL, SQL Server
5.5 | Manually Scheduled | Database Complete | Database design completion milestone | 0 days | 2026-08-03 | 2026-08-03 | 5.4 | Jemaine, Kaydyn, Ariana, Thersh, Wesley, Adrian | Milestone: Database Complete
6.0 | Manually Scheduled | System Development | Develop mobile frontend, backend and core modules | 20 days | 2026-08-04 | 2026-08-31 | 5.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | .NET MAUI, ASP.NET Core, Azure
6.1 | Manually Scheduled | Backend/API foundation | Develop ASP.NET Core backend and API foundation | 8 days | 2026-08-04 | 2026-08-13 | 5.5 | Kaydyn, Jemaine | ASP.NET Core, C#
6.2 | Manually Scheduled | Mobile frontend foundation | Develop .NET MAUI application structure and reusable UI | 8 days | 2026-08-04 | 2026-08-13 | 5.5 | Thersh, Adrian | .NET MAUI, XAML
6.3 | Manually Scheduled | Authentication module | Implement login, JWT and role-based authentication | 4 days | 2026-08-10 | 2026-08-13 | 6.1, 6.2 | Kaydyn, Wesley | ASP.NET Identity, JWT
6.4 | Manually Scheduled | Attendance module | Develop clock in/out and attendance history | 5 days | 2026-08-14 | 2026-08-20 | 6.3 | Adrian, Jemaine | .NET MAUI, Azure SQL
6.5 | Manually Scheduled | Task management module | Develop task assignment, updates and completion | 6 days | 2026-08-14 | 2026-08-21 | 6.3 | Thersh, Kaydyn | .NET MAUI, API
6.6 | Manually Scheduled | Inventory management module | Develop materials and low-stock functionality | 5 days | 2026-08-17 | 2026-08-21 | 6.1 | Jemaine, Wesley | Azure SQL, API
6.7 | Manually Scheduled | Reporting and document module | Develop reports, uploads and document storage | 5 days | 2026-08-24 | 2026-08-28 | 6.5 | Adrian, Thersh | Azure Blob Storage
6.8 | Manually Scheduled | Messaging and notifications | Develop chat and push notification features | 5 days | 2026-08-24 | 2026-08-28 | 6.5 | Kaydyn, Ariana | Firebase Cloud Messaging
6.9 | Manually Scheduled | Offline storage and automatic synchronisation | Implement SQLite offline queue and sync service | 6 days | 2026-08-24 | 2026-08-31 | 6.4, 6.5 | Jemaine, Kaydyn, Thersh | SQLite, Sync Service
6.10 | Manually Scheduled | Application Feature Complete | Core application development milestone | 0 days | 2026-08-31 | 2026-08-31 | 6.6, 6.7, 6.8, 6.9 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Application Feature Complete
7.0 | Manually Scheduled | Security Implementation | Implement application and data security controls | 6 days | 2026-09-01 | 2026-09-08 | 6.10 | Wesley, Kaydyn, Jemaine | Azure, ASP.NET Core
7.1 | Manually Scheduled | HTTPS/TLS configuration | Configure encrypted API communication | 1 day | 2026-09-01 | 2026-09-01 | 6.10 | Kaydyn, Wesley | HTTPS, TLS
7.2 | Manually Scheduled | Password hashing and secure authentication | Secure credentials and authentication logic | 1 day | 2026-09-02 | 2026-09-02 | 7.1 | Kaydyn, Wesley | ASP.NET Identity
7.3 | Manually Scheduled | Role-Based Access Control | Implement Administrator, Manager and Worker permissions | 2 days | 2026-09-03 | 2026-09-04 | 7.2 | Wesley, Jemaine | RBAC, JWT
7.4 | Manually Scheduled | Input validation and secure file handling | Implement server validation and upload restrictions | 1 day | 2026-09-07 | 2026-09-07 | 7.3 | Wesley, Thersh | Validation Tools
7.5 | Manually Scheduled | Audit logging and local-data encryption | Implement audit trail and protect offline data | 1 day | 2026-09-08 | 2026-09-08 | 7.4 | Wesley, Kaydyn | Azure Monitor, SQLite
7.6 | Manually Scheduled | Security Implementation Complete | Security implementation milestone | 0 days | 2026-09-08 | 2026-09-08 | 7.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Security Implementation Complete
8.0 | Manually Scheduled | Testing and Debugging | Test functionality, integration, security and compatibility | 13 days | 2026-09-09 | 2026-09-25 | 7.6 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | xUnit, Test Devices, GitHub
8.1 | Manually Scheduled | Functional testing | Test required features against acceptance criteria | 3 days | 2026-09-09 | 2026-09-11 | 7.6 | Wesley, Ariana | Test Cases
8.2 | Manually Scheduled | Integration testing | Test API, database, mobile and services together | 3 days | 2026-09-14 | 2026-09-16 | 8.1 | Wesley, Jemaine, Kaydyn | xUnit, Azure
8.3 | Manually Scheduled | Security testing | Test authentication, access control and common vulnerabilities | 2 days | 2026-09-17 | 2026-09-18 | 8.2 | Wesley, Kaydyn | Security Testing Tools
8.4 | Manually Scheduled | Device and offline compatibility testing | Test multiple screen sizes and poor/no connectivity | 2 days | 2026-09-21 | 2026-09-22 | 8.3 | Thersh, Adrian, Wesley | Android/iOS Devices
8.5 | Manually Scheduled | Fix identified defects | Resolve defects discovered during testing | 2 days | 2026-09-23 | 2026-09-24 | 8.4 | Kaydyn, Jemaine, Thersh | GitHub, IDE
8.6 | Manually Scheduled | User Acceptance Testing | Client validates system against business needs | 1 day | 2026-09-25 | 2026-09-25 | 8.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | UAT Checklist
8.7 | Manually Scheduled | Testing/UAT Complete | Testing phase completion milestone | 0 days | 2026-09-25 | 2026-09-25 | 8.6 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Testing Complete
9.0 | Manually Scheduled | Deployment | Prepare and deploy the production solution | 5 days | 2026-09-28 | 2026-10-02 | 8.7 | Kaydyn, Jemaine, Wesley | Azure, GitHub Actions
9.1 | Manually Scheduled | Prepare production environment | Configure Azure production resources | 1 day | 2026-09-28 | 2026-09-28 | 8.7 | Kaydyn, Jemaine | Azure
9.2 | Manually Scheduled | Configure CI/CD pipeline | Configure GitHub Actions deployment workflow | 1 day | 2026-09-29 | 2026-09-29 | 9.1 | Kaydyn, Wesley | GitHub Actions
9.3 | Manually Scheduled | Deploy backend and database | Deploy API and Azure SQL resources | 1 day | 2026-09-30 | 2026-09-30 | 9.2 | Kaydyn, Jemaine | Azure App Service, Azure SQL
9.4 | Manually Scheduled | Deploy/test mobile build | Prepare and validate production mobile build | 1 day | 2026-10-01 | 2026-10-01 | 9.3 | Thersh, Adrian | .NET MAUI
9.5 | Manually Scheduled | Verify production environment | Perform smoke tests and production checks | 1 day | 2026-10-02 | 2026-10-02 | 9.4 | Wesley, Kaydyn, Ariana, Jemaine, Thersh, Adrian | Azure Monitor
9.6 | Manually Scheduled | Deployment Complete | Deployment completion milestone | 0 days | 2026-10-02 | 2026-10-02 | 9.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Deployment Complete
10.0 | Manually Scheduled | Final Documentation and Handover | Complete technical, user and project documentation | 8 days | 2026-10-05 | 2026-10-14 | 9.6 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Word, Diagrams, User Manuals
10.1 | Manually Scheduled | Technical documentation | Document architecture, API, database and deployment | 2 days | 2026-10-05 | 2026-10-06 | 9.6 | Jemaine, Kaydyn | Word, API Documentation
10.2 | Manually Scheduled | User and training documentation | Prepare user guides and training material | 2 days | 2026-10-07 | 2026-10-08 | 10.1 | Ariana, Adrian | Word, Figma
10.3 | Manually Scheduled | Testing and deployment documentation | Document test evidence and deployment process | 1 day | 2026-10-09 | 2026-10-09 | 10.2 | Wesley | Word, Test Reports
10.4 | Manually Scheduled | Final report integration and review | Compile, format and quality-check final report | 3 days | 2026-10-12 | 2026-10-14 | 10.3 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Microsoft Word
10.5 | Manually Scheduled | Documentation Complete | Documentation completion milestone | 0 days | 2026-10-14 | 2026-10-14 | 10.4 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Documentation Complete
11.0 | Manually Scheduled | Final Presentation and Submission | Prepare final demonstration and submit project | 3 days | 2026-10-15 | 2026-10-19 | 10.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | PowerPoint, Demo Build
11.1 | Manually Scheduled | Prepare presentation and demonstration | Prepare slides and rehearse system demo | 2 days | 2026-10-15 | 2026-10-16 | 10.5 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | PowerPoint, Mobile App
11.2 | Manually Scheduled | Final system demonstration and checks | Perform final demo and submission readiness check | 1 day | 2026-10-19 | 2026-10-19 | 11.1 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | App, Projector
11.3 | Manually Scheduled | Final Submission | Submit completed WIL project | 0 days | 2026-10-19 | 2026-10-19 | 11.2 | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian | Milestone: Final Submission

## Project Summary
MCC Construction WIL Project | Summary
Project Start | 2026-05-06
Project End | 2026-10-19
Planned Working Days | 119
Team Members | Kaydyn, Ariana, Jemaine, Thersh, Wesley, Adrian
Primary Mobile Stack | .NET MAUI + ASP.NET Core + Azure SQL + SQLite
Prototype Tool | Figma
Offline Feature | Offline Mode with Automatic Synchronisation